## Pivot
|  |  | Units | Completed | Total in project
Row Labels | Workers | Sum of Duration (hours)
2025-04-01T08:00:00 | 1 | 9
Foundation | 1 | 9
Formwork | 1 | 9 | m2 |  | 500
2025-04-28T08:00:00 | 4 | 36
Foundation | 4 | 36
Formwork | 3 | 27 | m2 |  | 500
Setting out | 1 | 9 | m2 |  | 500
2025-04-29T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 |  | 500
2025-04-30T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 |  | 500
2025-05-01T08:00:00 | 4 | 36
Foundation | 4 | 36
Formwork | 4 | 36 | m2 |  | 500
2025-05-04T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 |  | 500
2025-05-05T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 |  | 500
2025-05-06T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn |  | 12
2025-05-07T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn |  | 12
2025-05-08T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn |  | 12
2025-05-11T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn |  | 12
2025-05-12T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn |  | 12
2025-05-13T08:00:00 | 6 | 54
Foundation | 6 | 54
Finishing | 6 | 54 | m2 |  | 500
2025-05-14T08:00:00 | 4 | 36
First floor | 1 | 9
Setting out | 1 | 9 | m2 |  | 450
Foundation | 3 | 27
Finishing | 3 | 27 | m2 |  | 500
2025-05-15T08:00:00 | 6 | 54
First floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 50
Foundation | 2 | 18
Finishing | 2 | 18 | m2 |  | 500
2025-05-16T08:00:00 | 2 | 18
Foundation | 2 | 18
Concreting | 2 | 18 | m3 |  | 80
2025-05-18T08:00:00 | 4 | 36
First floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 50
2025-05-19T08:00:00 | 6 | 54
First floor | 4 | 36
Assembly - Sandwich walls | 1 | 9 | elements |  | 50
Assembly - Solid walls | 3 | 27 | elements |  | 60
Foundation | 2 | 18
Concreting | 2 | 18 | m3 |  | 80
2025-05-20T08:00:00 | 9 | 81
First floor | 7 | 63
Assembly - Hollow core slabs | 3 | 27 | elements |  | 80
Assembly - Sandwich walls | 1 | 9 | elements |  | 60
Assembly - Solid walls | 3 | 27 | elements |  | 50
Foundation | 2 | 18
Concreting | 2 | 18 | m3 |  | 80
2025-05-21T08:00:00 | 5 | 45
First floor | 5 | 45
Assembly - Hollow core slabs | 5 | 45 | elements |  | 80
2025-05-22T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-05-25T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-05-26T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-05-27T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-05-28T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-05-29T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 5
2025-06-02T08:00:00 | 6 | 54
First floor | 6 | 54
Concreting | 6 | 54 | m3 |  | 12
2025-06-03T08:00:00 | 3 | 27
First floor | 2 | 18
Finishing work | 2 | 18 | m2 |  | 450
Second floor | 1 | 9
Setting out | 1 | 9 | m2 |  | 420
2025-06-04T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 |  | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 42
2025-06-05T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 |  | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 42
2025-06-08T08:00:00 | 3 | 27
First floor | 3 | 27
Finishing work | 3 | 27 | m2 |  | 450
2025-06-09T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 |  | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 42
2025-06-10T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 |  | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements |  | 42
2025-06-11T08:00:00 | 8 | 72
Second floor | 8 | 72
Assembly - Solid walls | 8 | 72 | elements |  | 82
2025-06-12T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-13T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-15T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-16T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-17T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-18T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn |  | 4
2025-06-19T08:00:00 | 5 | 45
Second floor | 5 | 45
Concreting | 5 | 45 | m3 |  | 14
2025-06-22T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 |  | 420
2025-06-23T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 |  | 420
2025-06-24T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 |  | 420
2025-06-25T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 |  | 420
Grand Total | 222 | 1998

## FinalTable
Row Labels | Workers | Sum of Duration (hours)
2025-04-01T08:00:00 | 1 | 9
Foundation | 1 | 9
Formwork | 1 | 9 | m2 | 500
2025-04-28T08:00:00 | 4 | 36
Foundation | 4 | 36
Formwork | 3 | 27 | m2 | 500
Setting out | 1 | 9
2025-04-29T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 | 500
2025-04-30T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 | 500
2025-05-01T08:00:00 | 4 | 36
Foundation | 4 | 36
Formwork | 4 | 36 | m2 | 500
2025-05-04T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 | 500
2025-05-05T08:00:00 | 5 | 45
Foundation | 5 | 45
Formwork | 5 | 45 | m2 | 500
2025-05-06T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn | 12
2025-05-07T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn | 12
2025-05-08T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn | 12
2025-05-11T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn | 12
2025-05-12T08:00:00 | 6 | 54
Foundation | 6 | 54
Reinforcement | 6 | 54 | tn | 12
2025-05-13T08:00:00 | 6 | 54
Foundation | 6 | 54
Finishing | 6 | 54 | m2 | 500
2025-05-14T08:00:00 | 4 | 36
First floor | 1 | 9
Setting out | 1 | 9 | m2 | 450
Foundation | 3 | 27
Finishing | 3 | 27 | m2 | 500
2025-05-15T08:00:00 | 6 | 54
First floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 50
Foundation | 2 | 18
Finishing | 2 | 18 | m2 | 500
2025-05-16T08:00:00 | 2 | 18
Foundation | 2 | 18
Concreting | 2 | 18 | m3 | 80
2025-05-18T08:00:00 | 4 | 36
First floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 50
2025-05-19T08:00:00 | 6 | 54
First floor | 4 | 36
Assembly - Sandwich walls | 1 | 9 | elements | 50
Assembly - Solid walls | 3 | 27 | elements | 60
Foundation | 2 | 18
Concreting | 2 | 18 | m3 | 80
2025-05-20T08:00:00 | 9 | 81
First floor | 7 | 63
Assembly - Hollow core slabs | 3 | 27 | elements | 80
Assembly - Sandwich walls | 1 | 9 | elements | 60
Assembly - Solid walls | 3 | 27 | elements | 50
Foundation | 2 | 18
Concreting | 2 | 18 | m3 | 80
2025-05-21T08:00:00 | 5 | 45
First floor | 5 | 45
Assembly - Hollow core slabs | 5 | 45 | elements | 80
2025-05-22T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-05-25T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-05-26T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-05-27T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-05-28T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-05-29T08:00:00 | 5 | 45
First floor | 5 | 45
Reinforcement | 5 | 45 | tn | 5
2025-06-02T08:00:00 | 6 | 54
First floor | 6 | 54
Concreting | 6 | 54 | m3 | 12
2025-06-03T08:00:00 | 3 | 27
First floor | 2 | 18
Finishing work | 2 | 18 | m2 | 450
Second floor | 1 | 9
Setting out | 1 | 9 | m2 | 420
2025-06-04T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 42
2025-06-05T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 42
2025-06-08T08:00:00 | 3 | 27
First floor | 3 | 27
Finishing work | 3 | 27 | m2 | 450
2025-06-09T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 42
2025-06-10T08:00:00 | 6 | 54
First floor | 2 | 18
Finishing work | 2 | 18 | m2 | 450
Second floor | 4 | 36
Assembly - Sandwich walls | 4 | 36 | elements | 42
2025-06-11T08:00:00 | 8 | 72
Second floor | 8 | 72
Assembly - Solid walls | 8 | 72 | elements | 82
2025-06-12T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-13T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-15T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-16T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-17T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-18T08:00:00 | 5 | 45
Second floor | 5 | 45
Reinforcement | 5 | 45 | tn | 4
2025-06-19T08:00:00 | 5 | 45
Second floor | 5 | 45
Concreting | 5 | 45 | m3 | 14
2025-06-22T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 | 420
2025-06-23T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 | 420
2025-06-24T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 | 420
2025-06-25T08:00:00 | 3 | 27
Second floor | 3 | 27
Finishing work | 3 | 27 | m2 | 420
Grand Total | 222 | 1998

## Attendance
id | worker_id | action | Start | Finish | location_id | work_id | worker_profession | Duration (hours) | Salary | Cost
1 | John Smith | Clock In | 2025-04-28T08:00:00 | 2025-04-28T17:00:00 | Foundation | Setting out | Assembler | 9 | 24.21 | 217.89
2 | Diana Wilson | Clock In | 2025-04-28T08:00:00 | 2025-04-28T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
3 | Eli Davies | Clock In | 2025-04-28T08:00:00 | 2025-04-28T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
4 | Ian Roberts | Clock In | 2025-04-28T08:00:00 | 2025-04-28T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
5 | John Smith | Clock In | 2025-04-29T08:00:00 | 2025-04-29T17:00:00 | Foundation | Formwork | Assembler | 9 | 24.21 | 217.89
6 | Diana Wilson | Clock In | 2025-04-29T08:00:00 | 2025-04-29T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
7 | Eli Davies | Clock In | 2025-04-29T08:00:00 | 2025-04-29T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
8 | Hannah Johnson | Clock In | 2025-04-29T08:00:00 | 2025-04-29T17:00:00 | Foundation | Formwork | Carpenter | 9 | 19.34 | 174.06
9 | Ian Roberts | Clock In | 2025-04-29T08:00:00 | 2025-04-29T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
10 | John Smith | Clock In | 2025-04-30T08:00:00 | 2025-04-30T17:00:00 | Foundation | Formwork | Assembler | 9 | 24.21 | 217.89
11 | Diana Wilson | Clock In | 2025-04-30T08:00:00 | 2025-04-30T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
12 | Eli Davies | Clock In | 2025-04-30T08:00:00 | 2025-04-30T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
13 | Hannah Johnson | Clock In | 2025-04-30T08:00:00 | 2025-04-30T17:00:00 | Foundation | Formwork | Carpenter | 9 | 19.34 | 174.06
14 | Ian Roberts | Clock In | 2025-04-30T08:00:00 | 2025-04-30T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
15 | John Smith | Clock In | 2025-04-01T08:00:00 | 2025-05-01T17:00:00 | Foundation | Formwork | Assembler | 9 | 24.21 | 217.89
16 | Diana Wilson | Clock In | 2025-05-01T08:00:00 | 2025-05-01T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
17 | Eli Davies | Clock In | 2025-05-01T08:00:00 | 2025-05-01T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
18 | Hannah Johnson | Clock In | 2025-05-01T08:00:00 | 2025-05-01T17:00:00 | Foundation | Formwork | Carpenter | 9 | 19.34 | 174.06
19 | Ian Roberts | Clock In | 2025-05-01T08:00:00 | 2025-05-01T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
20 | John Smith | Clock In | 2025-05-04T08:00:00 | 2025-05-04T17:00:00 | Foundation | Formwork | Assembler | 9 | 24.21 | 217.89
21 | Diana Wilson | Clock In | 2025-05-04T08:00:00 | 2025-05-04T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
22 | Eli Davies | Clock In | 2025-05-04T08:00:00 | 2025-05-04T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
23 | Hannah Johnson | Clock In | 2025-05-04T08:00:00 | 2025-05-04T17:00:00 | Foundation | Formwork | Carpenter | 9 | 19.34 | 174.06
24 | Ian Roberts | Clock In | 2025-05-04T08:00:00 | 2025-05-04T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
25 | John Smith | Clock In | 2025-05-05T08:00:00 | 2025-05-05T17:00:00 | Foundation | Formwork | Assembler | 9 | 24.21 | 217.89
26 | Diana Wilson | Clock In | 2025-05-05T08:00:00 | 2025-05-05T17:00:00 | Foundation | Formwork | General labourer | 9 | 18.72 | 168.48
27 | Eli Davies | Clock In | 2025-05-05T08:00:00 | 2025-05-05T17:00:00 | Foundation | Formwork | General labourer | 9 | 17.68 | 159.12
28 | Hannah Johnson | Clock In | 2025-05-05T08:00:00 | 2025-05-05T17:00:00 | Foundation | Formwork | Carpenter | 9 | 19.34 | 174.06
29 | Ian Roberts | Clock In | 2025-05-05T08:00:00 | 2025-05-05T17:00:00 | Foundation | Formwork | Site Manager | 9 | 23.89 | 215.01
30 | John Smith | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | Assembler | 9 | 24.21 | 217.89
31 | Diana Wilson | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 18.72 | 168.48
32 | Eli Davies | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 17.68 | 159.12
33 | Fiona Evans | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
34 | George Thomas | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
35 | Ian Roberts | Clock In | 2025-05-06T08:00:00 | 2025-05-06T17:00:00 | Foundation | Reinforcement | Site Manager | 9 | 23.89 | 215.01
36 | John Smith | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | Assembler | 9 | 24.21 | 217.89
37 | Diana Wilson | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 18.72 | 168.48
38 | Eli Davies | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 17.68 | 159.12
39 | Fiona Evans | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
40 | George Thomas | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
41 | Ian Roberts | Clock In | 2025-05-07T08:00:00 | 2025-05-07T17:00:00 | Foundation | Reinforcement | Site Manager | 9 | 23.89 | 215.01
42 | John Smith | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | Assembler | 9 | 24.21 | 217.89
43 | Diana Wilson | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 18.72 | 168.48
44 | Eli Davies | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 17.68 | 159.12
45 | Fiona Evans | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
46 | George Thomas | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
47 | Ian Roberts | Clock In | 2025-05-08T08:00:00 | 2025-05-08T17:00:00 | Foundation | Reinforcement | Site Manager | 9 | 23.89 | 215.01
48 | John Smith | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | Assembler | 9 | 24.21 | 217.89
49 | Diana Wilson | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 18.72 | 168.48
50 | Eli Davies | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 17.68 | 159.12
51 | Fiona Evans | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
52 | George Thomas | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
53 | Ian Roberts | Clock In | 2025-05-11T08:00:00 | 2025-05-11T17:00:00 | Foundation | Reinforcement | Site Manager | 9 | 23.89 | 215.01
54 | John Smith | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | Assembler | 9 | 24.21 | 217.89
55 | Diana Wilson | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 18.72 | 168.48
56 | Eli Davies | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | General labourer | 9 | 17.68 | 159.12
57 | Fiona Evans | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
58 | George Thomas | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
59 | Ian Roberts | Clock In | 2025-05-12T08:00:00 | 2025-05-12T17:00:00 | Foundation | Reinforcement | Site Manager | 9 | 23.89 | 215.01
60 | John Smith | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | Assembler | 9 | 24.21 | 217.89
61 | Fiona Evans | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | Steel fixer | 9 | 18.49 | 166.41
62 | George Thomas | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | Steel fixer | 9 | 21.3 | 191.7
63 | Diana Wilson | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | General labourer | 9 | 18.72 | 168.48
64 | Eli Davies | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | General labourer | 9 | 17.68 | 159.12
65 | Ian Roberts | Clock In | 2025-05-13T08:00:00 | 2025-05-13T17:00:00 | Foundation | Finishing | Site Manager | 9 | 23.89 | 215.01
66 | John Smith | Clock In | 2025-05-14T08:00:00 | 2025-05-14T17:00:00 | Foundation | Finishing | Assembler | 9 | 24.21 | 217.89
67 | Diana Wilson | Clock In | 2025-05-14T08:00:00 | 2025-05-14T17:00:00 | Foundation | Finishing | General labourer | 9 | 18.72 | 168.48
68 | Eli Davies | Clock In | 2025-05-14T08:00:00 | 2025-05-14T17:00:00 | Foundation | Finishing | General labourer | 9 | 17.68 | 159.12
69 | Ian Roberts | Clock In | 2025-05-14T08:00:00 | 2025-05-14T17:00:00 | First floor | Setting out | Site Manager | 9 | 23.89 | 215.01
70 | Diana Wilson | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | Foundation | Finishing | General labourer | 9 | 18.72 | 168.48
71 | Eli Davies | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | Foundation | Finishing | General labourer | 9 | 17.68 | 159.12
72 | Ian Roberts | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | First floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
73 | John Smith | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
74 | Alice Brown | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
75 | Bob Taylor | Clock In | 2025-05-15T08:00:00 | 2025-05-15T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
76 | Diana Wilson | Clock In | 2025-05-16T08:00:00 | 2025-05-16T17:00:00 | Foundation | Concreting | General labourer | 9 | 18.72 | 168.48
77 | Eli Davies | Clock In | 2025-05-16T08:00:00 | 2025-05-16T17:00:00 | Foundation | Concreting | General labourer | 9 | 17.68 | 159.12
78 | Ian Roberts | Clock In | 2025-05-18T08:00:00 | 2025-05-18T17:00:00 | First floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
79 | John Smith | Clock In | 2025-05-18T08:00:00 | 2025-05-18T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
80 | Alice Brown | Clock In | 2025-05-18T08:00:00 | 2025-05-18T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
81 | Bob Taylor | Clock In | 2025-05-18T08:00:00 | 2025-05-18T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
82 | John Smith | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
83 | Alice Brown | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | First floor | Assembly - Solid walls | Assembler | 9 | 24.56 | 221.04
84 | Bob Taylor | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | First floor | Assembly - Solid walls | Assembler | 9 | 24.99 | 224.91
85 | Diana Wilson | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | Foundation | Concreting | General labourer | 9 | 18.72 | 168.48
86 | Eli Davies | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | Foundation | Concreting | General labourer | 9 | 17.68 | 159.12
87 | Ian Roberts | Clock In | 2025-05-19T08:00:00 | 2025-05-19T17:00:00 | First floor | Assembly - Solid walls | Site Manager | 9 | 23.89 | 215.01
88 | John Smith | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
89 | Alice Brown | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Solid walls | Assembler | 9 | 24.56 | 221.04
90 | Bob Taylor | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Solid walls | Assembler | 9 | 24.99 | 224.91
91 | Diana Wilson | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | Foundation | Concreting | General labourer | 9 | 18.72 | 168.48
92 | Eli Davies | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | Foundation | Concreting | General labourer | 9 | 17.68 | 159.12
93 | Ian Roberts | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Solid walls | Site Manager | 9 | 23.89 | 215.01
94 | John Smith | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Hollow core slabs | Assembler | 9 | 24.21 | 217.89
95 | Alice Brown | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Hollow core slabs | Assembler | 9 | 24.56 | 221.04
96 | Bob Taylor | Clock In | 2025-05-20T08:00:00 | 2025-05-20T17:00:00 | First floor | Assembly - Hollow core slabs | Assembler | 9 | 24.99 | 224.91
97 | Diana Wilson | Clock In | 2025-05-21T08:00:00 | 2025-05-21T17:00:00 | First floor | Assembly - Hollow core slabs | General labourer | 9 | 18.72 | 168.48
98 | Eli Davies | Clock In | 2025-05-21T08:00:00 | 2025-05-21T17:00:00 | First floor | Assembly - Hollow core slabs | General labourer | 9 | 17.68 | 159.12
99 | Fiona Evans | Clock In | 2025-05-21T08:00:00 | 2025-05-21T17:00:00 | First floor | Assembly - Hollow core slabs | Steel fixer | 9 | 18.49 | 166.41
100 | George Thomas | Clock In | 2025-05-21T08:00:00 | 2025-05-21T17:00:00 | First floor | Assembly - Hollow core slabs | Steel fixer | 9 | 21.3 | 191.7
101 | Ian Roberts | Clock In | 2025-05-21T08:00:00 | 2025-05-21T17:00:00 | First floor | Assembly - Hollow core slabs | Site Manager | 9 | 23.89 | 215.01
102 | Diana Wilson | Clock In | 2025-05-22T08:00:00 | 2025-05-22T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
103 | Eli Davies | Clock In | 2025-05-22T08:00:00 | 2025-05-22T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
104 | Fiona Evans | Clock In | 2025-05-22T08:00:00 | 2025-05-22T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
105 | George Thomas | Clock In | 2025-05-22T08:00:00 | 2025-05-22T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
106 | Ian Roberts | Clock In | 2025-05-22T08:00:00 | 2025-05-22T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
107 | Diana Wilson | Clock In | 2025-05-25T08:00:00 | 2025-05-25T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
108 | Eli Davies | Clock In | 2025-05-25T08:00:00 | 2025-05-25T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
109 | Fiona Evans | Clock In | 2025-05-25T08:00:00 | 2025-05-25T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
110 | George Thomas | Clock In | 2025-05-25T08:00:00 | 2025-05-25T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
111 | Ian Roberts | Clock In | 2025-05-25T08:00:00 | 2025-05-25T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
112 | Diana Wilson | Clock In | 2025-05-26T08:00:00 | 2025-05-26T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
113 | Eli Davies | Clock In | 2025-05-26T08:00:00 | 2025-05-26T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
114 | Fiona Evans | Clock In | 2025-05-26T08:00:00 | 2025-05-26T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
115 | George Thomas | Clock In | 2025-05-26T08:00:00 | 2025-05-26T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
116 | Ian Roberts | Clock In | 2025-05-26T08:00:00 | 2025-05-26T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
117 | Diana Wilson | Clock In | 2025-05-27T08:00:00 | 2025-05-27T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
118 | Eli Davies | Clock In | 2025-05-27T08:00:00 | 2025-05-27T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
119 | Fiona Evans | Clock In | 2025-05-27T08:00:00 | 2025-05-27T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
120 | George Thomas | Clock In | 2025-05-27T08:00:00 | 2025-05-27T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
121 | Ian Roberts | Clock In | 2025-05-27T08:00:00 | 2025-05-27T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
122 | Diana Wilson | Clock In | 2025-05-28T08:00:00 | 2025-05-28T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
123 | Eli Davies | Clock In | 2025-05-28T08:00:00 | 2025-05-28T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
124 | Fiona Evans | Clock In | 2025-05-28T08:00:00 | 2025-05-28T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
125 | George Thomas | Clock In | 2025-05-28T08:00:00 | 2025-05-28T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
126 | Ian Roberts | Clock In | 2025-05-28T08:00:00 | 2025-05-28T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
127 | Diana Wilson | Clock In | 2025-05-29T08:00:00 | 2025-05-29T17:00:00 | First floor | Reinforcement | General labourer | 9 | 18.72 | 168.48
128 | Eli Davies | Clock In | 2025-05-29T08:00:00 | 2025-05-29T17:00:00 | First floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
129 | Fiona Evans | Clock In | 2025-05-29T08:00:00 | 2025-05-29T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
130 | George Thomas | Clock In | 2025-05-29T08:00:00 | 2025-05-29T17:00:00 | First floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
131 | Ian Roberts | Clock In | 2025-05-29T08:00:00 | 2025-05-29T17:00:00 | First floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
132 | John Smith | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | Assembler | 9 | 24.21 | 217.89
133 | Diana Wilson | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | General labourer | 9 | 18.72 | 168.48
134 | Eli Davies | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | General labourer | 9 | 17.68 | 159.12
135 | Fiona Evans | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | Steel fixer | 9 | 18.49 | 166.41
136 | George Thomas | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | Steel fixer | 9 | 21.3 | 191.7
137 | Ian Roberts | Clock In | 2025-06-02T08:00:00 | 2025-06-02T17:00:00 | First floor | Concreting | Site Manager | 9 | 23.89 | 215.01
138 | Diana Wilson | Clock In | 2025-06-03T08:00:00 | 2025-06-03T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
139 | Eli Davies | Clock In | 2025-06-03T08:00:00 | 2025-06-03T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
140 | Ian Roberts | Clock In | 2025-06-03T08:00:00 | 2025-06-03T17:00:00 | Second floor | Setting out | Site Manager | 9 | 23.89 | 215.01
141 | Diana Wilson | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
142 | Eli Davies | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
143 | John Smith | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
144 | Alice Brown | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
145 | Bob Taylor | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
146 | Ian Roberts | Clock In | 2025-06-04T08:00:00 | 2025-06-04T17:00:00 | Second floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
147 | Diana Wilson | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
148 | Eli Davies | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
149 | John Smith | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
150 | Alice Brown | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
151 | Bob Taylor | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
152 | Ian Roberts | Clock In | 2025-06-05T08:00:00 | 2025-06-05T17:00:00 | Second floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
153 | Diana Wilson | Clock In | 2025-06-08T08:00:00 | 2025-06-08T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
154 | Eli Davies | Clock In | 2025-06-08T08:00:00 | 2025-06-08T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
155 | Ian Roberts | Clock In | 2025-06-08T08:00:00 | 2025-06-08T17:00:00 | First floor | Finishing work | Site Manager | 9 | 23.89 | 215.01
156 | John Smith | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
157 | Alice Brown | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
158 | Bob Taylor | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
159 | Diana Wilson | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
160 | Eli Davies | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
161 | Ian Roberts | Clock In | 2025-06-09T08:00:00 | 2025-06-09T17:00:00 | Second floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
162 | John Smith | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.21 | 217.89
163 | Alice Brown | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.56 | 221.04
164 | Bob Taylor | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | Second floor | Assembly - Sandwich walls | Assembler | 9 | 24.99 | 224.91
165 | Diana Wilson | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | First floor | Finishing work | General labourer | 9 | 18.72 | 168.48
166 | Eli Davies | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | First floor | Finishing work | General labourer | 9 | 17.68 | 159.12
167 | Ian Roberts | Clock In | 2025-06-10T08:00:00 | 2025-06-10T17:00:00 | Second floor | Assembly - Sandwich walls | Site Manager | 9 | 23.89 | 215.01
168 | Alice Brown | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Assembler | 9 | 24.56 | 221.04
169 | Bob Taylor | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Assembler | 9 | 24.99 | 224.91
170 | John Smith | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Assembler | 9 | 24.21 | 217.89
171 | Diana Wilson | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | General labourer | 9 | 18.72 | 168.48
172 | Eli Davies | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | General labourer | 9 | 17.68 | 159.12
173 | Fiona Evans | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Steel fixer | 9 | 18.49 | 166.41
174 | George Thomas | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Steel fixer | 9 | 21.3 | 191.7
175 | Ian Roberts | Clock In | 2025-06-11T08:00:00 | 2025-06-11T17:00:00 | Second floor | Assembly - Solid walls | Site Manager | 9 | 23.89 | 215.01
176 | Fiona Evans | Clock In | 2025-06-12T08:00:00 | 2025-06-12T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
177 | George Thomas | Clock In | 2025-06-12T08:00:00 | 2025-06-12T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
178 | Eli Davies | Clock In | 2025-06-12T08:00:00 | 2025-06-12T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
179 | Ian Roberts | Clock In | 2025-06-12T08:00:00 | 2025-06-12T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
180 | John Smith | Clock In | 2025-06-12T08:00:00 | 2025-06-12T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
181 | Fiona Evans | Clock In | 2025-06-13T08:00:00 | 2025-06-13T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
182 | George Thomas | Clock In | 2025-06-13T08:00:00 | 2025-06-13T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
183 | Eli Davies | Clock In | 2025-06-13T08:00:00 | 2025-06-13T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
184 | Ian Roberts | Clock In | 2025-06-13T08:00:00 | 2025-06-13T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
185 | John Smith | Clock In | 2025-06-13T08:00:00 | 2025-06-13T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
186 | Fiona Evans | Clock In | 2025-06-15T08:00:00 | 2025-06-15T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
187 | George Thomas | Clock In | 2025-06-15T08:00:00 | 2025-06-15T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
188 | Eli Davies | Clock In | 2025-06-15T08:00:00 | 2025-06-15T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
189 | Ian Roberts | Clock In | 2025-06-15T08:00:00 | 2025-06-15T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
190 | John Smith | Clock In | 2025-06-15T08:00:00 | 2025-06-15T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
191 | Fiona Evans | Clock In | 2025-06-16T08:00:00 | 2025-06-16T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
192 | George Thomas | Clock In | 2025-06-16T08:00:00 | 2025-06-16T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
193 | Eli Davies | Clock In | 2025-06-16T08:00:00 | 2025-06-16T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
194 | Ian Roberts | Clock In | 2025-06-16T08:00:00 | 2025-06-16T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
195 | John Smith | Clock In | 2025-06-16T08:00:00 | 2025-06-16T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
196 | Fiona Evans | Clock In | 2025-06-17T08:00:00 | 2025-06-17T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
197 | George Thomas | Clock In | 2025-06-17T08:00:00 | 2025-06-17T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
198 | Eli Davies | Clock In | 2025-06-17T08:00:00 | 2025-06-17T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
199 | Ian Roberts | Clock In | 2025-06-17T08:00:00 | 2025-06-17T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
200 | John Smith | Clock In | 2025-06-17T08:00:00 | 2025-06-17T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
201 | Fiona Evans | Clock In | 2025-06-18T08:00:00 | 2025-06-18T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 18.49 | 166.41
202 | George Thomas | Clock In | 2025-06-18T08:00:00 | 2025-06-18T17:00:00 | Second floor | Reinforcement | Steel fixer | 9 | 21.3 | 191.7
203 | Eli Davies | Clock In | 2025-06-18T08:00:00 | 2025-06-18T17:00:00 | Second floor | Reinforcement | General labourer | 9 | 17.68 | 159.12
204 | Ian Roberts | Clock In | 2025-06-18T08:00:00 | 2025-06-18T17:00:00 | Second floor | Reinforcement | Site Manager | 9 | 23.89 | 215.01
205 | John Smith | Clock In | 2025-06-18T08:00:00 | 2025-06-18T17:00:00 | Second floor | Reinforcement | Assembler | 9 | 24.21 | 217.89
206 | Fiona Evans | Clock In | 2025-06-19T08:00:00 | 2025-06-19T17:00:00 | Second floor | Concreting | Steel fixer | 9 | 18.49 | 166.41
207 | George Thomas | Clock In | 2025-06-19T08:00:00 | 2025-06-19T17:00:00 | Second floor | Concreting | Steel fixer | 9 | 21.3 | 191.7
208 | Eli Davies | Clock In | 2025-06-19T08:00:00 | 2025-06-19T17:00:00 | Second floor | Concreting | General labourer | 9 | 17.68 | 159.12
209 | Ian Roberts | Clock In | 2025-06-19T08:00:00 | 2025-06-19T17:00:00 | Second floor | Concreting | Site Manager | 9 | 23.89 | 215.01
210 | John Smith | Clock In | 2025-06-19T08:00:00 | 2025-06-19T17:00:00 | Second floor | Concreting | Assembler | 9 | 24.21 | 217.89
211 | Diana Wilson | Clock In | 2025-06-22T08:00:00 | 2025-06-22T17:00:00 | Second floor | Finishing work | General labourer | 9 | 18.72 | 168.48
212 | Eli Davies | Clock In | 2025-06-22T08:00:00 | 2025-06-22T17:00:00 | Second floor | Finishing work | General labourer | 9 | 17.68 | 159.12
213 | Ian Roberts | Clock In | 2025-06-22T08:00:00 | 2025-06-22T17:00:00 | Second floor | Finishing work | Site Manager | 9 | 23.89 | 215.01
214 | Diana Wilson | Clock In | 2025-06-23T08:00:00 | 2025-06-23T17:00:00 | Second floor | Finishing work | General labourer | 9 | 18.72 | 168.48
215 | Eli Davies | Clock In | 2025-06-23T08:00:00 | 2025-06-23T17:00:00 | Second floor | Finishing work | General labourer | 9 | 17.68 | 159.12
216 | Ian Roberts | Clock In | 2025-06-23T08:00:00 | 2025-06-23T17:00:00 | Second floor | Finishing work | Site Manager | 9 | 23.89 | 215.01
217 | Diana Wilson | Clock In | 2025-06-24T08:00:00 | 2025-06-24T17:00:00 | Second floor | Finishing work | General labourer | 9 | 18.72 | 168.48
218 | Eli Davies | Clock In | 2025-06-24T08:00:00 | 2025-06-24T17:00:00 | Second floor | Finishing work | General labourer | 9 | 17.68 | 159.12
219 | Ian Roberts | Clock In | 2025-06-24T08:00:00 | 2025-06-24T17:00:00 | Second floor | Finishing work | Site Manager | 9 | 23.89 | 215.01
220 | Diana Wilson | Clock In | 2025-06-25T08:00:00 | 2025-06-25T17:00:00 | Second floor | Finishing work | General labourer | 9 | 18.72 | 168.48
221 | Eli Davies | Clock In | 2025-06-25T08:00:00 | 2025-06-25T17:00:00 | Second floor | Finishing work | General labourer | 9 | 17.68 | 159.12
222 | Ian Roberts | Clock In | 2025-06-25T08:00:00 | 2025-06-25T17:00:00 | Second floor | Finishing work | Site Manager | 9 | 23.89 | 215.01
462 | 9 | Clock Out |  |  | 3 | 5 | Site Manager